## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Kelvin Tawe | Lead Developer & Learning Rate Researcher
Samuel Mwania | Gamma/Batch Size Researcher & Integration Lead
Divine Birasa | Exploration Schedule Researcher
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Set up repository, config.py, train.py, play.py, evaluate.py, compare_policies.py | Kelvin Tawe | 2026-07-06 | Completed | Yes | Created the core codebase with CLI-driven training, preset support, evaluation modes, and play/record scripts
| Run 10 learning rate experiments (1e-6 to 1e-2) | Kelvin Tawe | 2026-07-12 | Completed | Yes | Swept LR across 4 orders of magnitude. Best: 3e-4 (highest AUC, lowest late variance). Documented in M1 notebook
| Run 5 gamma experiments (0.90 to 0.999) and 5 batch size experiments (8 to 256) | Samuel Mwania | 2026-07-12 | Completed | Yes | Best gamma=0.90 (AUC=22.13), best batch=64 (AUC=21.67). Gamma=0.999 collapsed catastrophically. Documented in Samuel notebook
| Run 10 exploration schedule experiments (epsilon decay and floor variations) | Divine Birasa | 2026-07-13 | Completed | Yes | Varied epsilon fraction (0.02-0.50) and floor (0.0-0.30). Best: frac=0.10, floor=0.20. Documented in Divine notebook
| Run CNN vs MLP policy comparison (200k steps each) | Samuel Mwania | 2026-07-13 | Completed | Yes | Trained CnnPolicy and MlpPolicy under identical conditions. CNN converged faster, validating convolutional architecture
| Train final combined model (500k steps with best hyperparameters from all members) | Samuel Mwania | 2026-07-19 | Completed | Yes | Combined lr=3e-4, gamma=0.90, batch=64, eps_frac=0.10, eps_floor=0.20. Result: mean_reward=22.5, AUC=22.25
| Create individual experiment notebooks with analysis and visualisations | Kelvin Tawe, Samuel Mwania, Divine Birasa | 2026-07-14 | Completed | Yes | M1_Learning_Rate_Experiments.ipynb, Samuel_Mwania_Experiments.ipynb, Divine_epsilon_sweep.ipynb
| Generate master group notebook, record gameplay video, write comprehensive README | Samuel Mwania | 2026-07-19 | Completed | Yes | Freeway_DQN_Group_Submission.ipynb (41 cells, all 30 experiments). README with full HP tables and contribution breakdown
| Fill contribution sheet and submit (zip + GitHub URL) | Samuel Mwania | 2026-07-19 | Completed | Yes | Completed team task sheet. Zipped repo and submitted via portal. GitHub URL submitted as second attempt
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-07-05 | Project kickoff and environment selection | Kelvin Tawe | Kelvin Tawe, Samuel Mwania, Divine Birasa | Chose ALE/Freeway-v5. Assigned HP axes: Kelvin=LR, Samuel=gamma+batch, Divine=exploration. Set shared baseline config | Kelvin to set up repo and core scripts. All to review DQN paper
2026-07-10 | Experiment planning and compute budget | Samuel Mwania | Kelvin Tawe, Samuel Mwania, Divine Birasa | Reviewed EXPERIMENTS.md plan. Agreed on 150k-step sweep budget. Defined AUC, late_std, steps_to_threshold metrics | Each member runs their 10 experiments on Colab and pushes results
2026-07-13 | Results review and best-value selection | Samuel Mwania | Kelvin Tawe, Samuel Mwania, Divine Birasa | Reviewed all 30 results. Selected best values: lr=3e-4, gamma=0.90, batch=64, eps_frac=0.10, eps_floor=0.20 | Samuel to train final combined model and run CNN vs MLP comparison
2026-07-18 | Final notebook review and presentation prep | Samuel Mwania | Kelvin Tawe, Samuel Mwania, Divine Birasa | Reviewed master notebook structure. Agreed on presentation flow. Rehearsed Q&A on Bellman equation and exploration | Samuel to generate final notebook, record video, and submit
[Date] |  | [Name] | [List of Attendees] | [Summary of Discussion] | [Follow-up Actions]